## Year-1 Schedule
Pratt Richmond → KWE Sterling — Year-1 Restock Schedule
Every PO and delivery, Jul 2026 – Jul 2027, from the validated daily inventory simulation (100 boxes/month usage). Highlighted rows = Pratt MOQ POs / go-live.
Date | Event | Part A | Part B | Boxes | Pallets to KWE | Richmond A after | Richmond B after | Notes
2026-07-08 | Pratt PO-1 placed | 500 | 450 | 175 |  |  |  | MOQ 15 plt held in Richmond + first box order; in stock 2026-07-22
2026-07-22 | Go-live delivery to KWE | 100 | 90 | 175 | 5 | 400 | 360 | 2 plt A + 1 plt B + 2 plt boxes
2026-08-19 | Truck delivery to KWE | 50 | 90 |  | 2 | 350 | 270
2026-08-19 | Box PO placed |  |  | 175 |  |  |  | 2-week lead; arrives on truck 2026-09-02
2026-09-02 | Truck delivery to KWE | 50 | 90 | 175 | 4 | 300 | 180
2026-09-02 | Pratt PO-2 placed | 450 | 540 |  |  |  |  | MOQ 15 plt for Richmond hold; in stock 2026-09-30
2026-09-16 | Truck delivery to KWE | 50 |  |  | 1 | 250 | 180
2026-09-30 | Truck delivery to KWE | 50 | 90 |  | 2 | 650 | 630
2026-10-14 | Truck delivery to KWE | 50 |  |  | 1 | 600 | 630
2026-10-14 | Box PO placed |  |  | 175 |  |  |  | 2-week lead; arrives on truck 2026-10-28
2026-10-28 | Truck delivery to KWE |  | 90 | 175 | 3 | 600 | 540
2026-11-11 | Truck delivery to KWE | 100 |  |  | 2 | 500 | 540
2026-11-25 | Truck delivery to KWE |  | 90 |  | 1 | 500 | 450
2026-12-09 | Truck delivery to KWE | 100 |  |  | 2 | 400 | 450
2026-12-09 | Box PO placed |  |  | 175 |  |  |  | 2-week lead; arrives on truck 2026-12-23
2026-12-23 | Truck delivery to KWE |  | 90 | 175 | 3 | 400 | 360
2027-01-06 | Truck delivery to KWE | 50 |  |  | 1 | 350 | 360
2027-01-20 | Truck delivery to KWE | 50 | 90 |  | 2 | 300 | 270
2027-01-20 | Box PO placed |  |  | 175 |  |  |  | 2-week lead; arrives on truck 2027-02-03
2027-02-03 | Truck delivery to KWE | 50 |  | 175 | 3 | 250 | 270
2027-02-17 | Truck delivery to KWE | 50 | 90 |  | 2 | 200 | 180
2027-02-17 | Pratt PO-3 placed | 500 | 450 |  |  |  |  | MOQ 15 plt for Richmond hold; in stock 2027-03-17
2027-03-03 | Truck delivery to KWE | 50 |  |  | 1 | 150 | 180
2027-03-17 | Truck delivery to KWE | 50 | 90 |  | 2 | 600 | 540
2027-03-17 | Box PO placed |  |  | 175 |  |  |  | 2-week lead; arrives on truck 2027-03-31
2027-03-31 | Truck delivery to KWE | 50 |  | 175 | 3 | 550 | 540
2027-04-14 | Truck delivery to KWE | 50 | 90 |  | 2 | 500 | 450
2027-05-12 | Truck delivery to KWE | 100 | 90 |  | 3 | 400 | 360
2027-05-12 | Box PO placed |  |  | 175 |  |  |  | 2-week lead; arrives on truck 2027-05-26
2027-05-26 | Truck delivery to KWE |  |  | 175 | 2 | 400 | 360
2027-06-09 | Truck delivery to KWE | 50 | 90 |  | 2 | 350 | 270
2027-06-23 | Truck delivery to KWE | 50 |  |  | 1 | 300 | 270
2027-07-07 | Truck delivery to KWE | 50 | 90 |  | 2 | 250 | 180
2027-07-07 | Box PO placed |  |  | 175 |  |  |  | 2-week lead; arrives on truck 2027-07-21
2027-07-07 | Pratt PO-4 placed | 450 | 540 |  |  |  |  | MOQ 15 plt for Richmond hold; in stock 2027-08-04
2027-07-21 | Truck delivery to KWE | 50 |  | 175 | 3 | 200 | 180

## Cadence & Triggers
Operating Rules — Reorder Triggers
A truck runs Richmond → Sterling every 2 weeks; the load is decided by on-hand stock at KWE on truck day. MOQ mix ask: alternate 10A/5B → 9A/6B so parts stay balanced at 1:1 usage.
Part | Add to truck when Sterling on-hand is… | Quantity | Effective cadence
Part A | ≤ 60 units (≤ 25 → send 2 pallets) | 1 pallet (50 units) | ~every biweekly truck · 2 plt/month · 24 plt/year
Part B | ≤ 75 units | 1 pallet (90 units) | ~every other truck · ~13–14 plt/year
Boxes | Projected ≤ 90 at next truck (≈ on-hand ≤ 135 today) → place PO now (2-week lead) | 175 (2 pallets) | every ~7½ weeks · 7 POs/year
New Pratt MOQ PO | Richmond hold ≤ 180 units of Part B (2 pallets) | MOQ 15 pallets | every ~4.5–5 months · ~3/year

## Quote & Assumptions
Pratt Quote & Model Assumptions
Source: Pratt Industries quote (Chillin Liners / MP Global 2″ recycled-paper insulation).
Item | Value | Notes
Custom box OD 24x16x18 | $5.50 each | Order qty 175 = 2 pallets; 2-week lead; Pratt will NOT hold boxes
Insulation set (A+B) | $11.60 / set | Confirm: 1 set = one Part A + one Part B
Insulation MOQ | 15 pallets | 10 plt Part A (500 units) + 5 plt Part B (450 units); Pratt holds in Richmond
Sub-MOQ option | +$400 / order | Min 4 plt A (200) + 3 plt B (270) — fallback only
Box pack-out | ~80–90 / pallet | 175 boxes = 2 pallets
Part A pack-out | 50 / pallet
Part B pack-out | 90 / pallet
Usage rate | 100 boxes / month
KWE Sterling capacity | ~6 pallets | UNCONFIRMED — user guess; confirm with KWE
Pratt holding fee (insulation) | TBD | Requested 7/7 — chase
Freight Richmond → Sterling | TBD | Not yet shared; decides biweekly vs monthly trucks
Insulation production lead | 4 weeks (assumed) | Unconfirmed; boxes quoted at 2 weeks
Richmond release notice | ≤ 2 weeks (assumed) | Confirm with Pratt

## Costs
Materials Spend — excludes freight & Pratt holding fee (both TBD)
Sub-MOQ fallback: using the +$400 option ~5–6×/year adds ~$2,000–2,400 (≈17% on insulation spend).
Line | Monthly | Annual | Per PO
Boxes — 100 × $5.50 | 550 | 6600 | $962.50 per 175-box PO
Insulation — 100 sets × $11.60 | 1160 | 13920 | ~$5,220–5,800 per MOQ PO (billing basis TBC)
Total materials (≈ $17.10 per shipped box) | 1710 | 20520