## GUIDE
PART-SUPPLIER RISK MODEL
One simple tool: decompose each model into its parts (tissue and non-tissue), link every part to its supplier, and score the risk of each part-supplier combination.
HOW TO USE (4 steps)
1. MODELS - add the model / project (one row). A model may have tissue parts, non-tissue parts, or both.
2. SUPPLIERS - add the supplier and give it its two 1-5 scores (Supplier Stability, External & Location). You do this once per supplier.
3. PART_RISK - one row per part-supplier combo: pick the model, type the part, pick the type and supplier, score the three part criteria (1-5), score Impact (1-5), and set a Red Flag only if one applies. Likelihood, Risk and Band calculate automatically.
4. DASHBOARD - select a model to see its decomposition ranked by risk; review the Top 10 across all models; write mitigations back into the Notes column of PART_RISK.
HOW THE SCORE WORKS
Likelihood (1-5) = weighted average of: Sourcing & Backup 25%, Quality & Compliance 25%, Capacity & Delivery 20%, Supplier Stability 20%, External & Location 10%.
Risk (1-25) = Likelihood x Impact. Bands: >= 15 CRITICAL (act now) ¦ 7 - 14.9 MONITOR (watch + contingency) ¦ < 7 LOW (routine).
A Red Flag forces CRITICAL regardless of the numbers (e.g. APHIS/permit lapse on a tissue part, EOL on a COTS part). Full anchors and definitions: SCORING_GUIDE sheet.
LEGEND
Cream cells = you enter or pick from a dropdown. Gray cells = automatic, do not type in them.
Scores always read the same way: 1 = low risk ... 5 = high risk. If you can't answer, leave blank - the row shows NOT SCORED.
Example data is included (2 models, 6 suppliers, 6 part rows, marked EXAMPLE) to show the format - replace it with your own.
SUGGESTED CADENCE
Score new part-supplier combos at sourcing time; re-score CRITICAL quarterly, MONITOR twice a year, LOW yearly, and any time a red-flag event happens. Update Last_Reviewed every time - a dated, ongoing monitoring record is what ISO 13485 / FDA QMSR supplier controls expect.

## DASHBOARD
PART-SUPPLIER RISK DASHBOARD
Everything updates automatically from PART_RISK, SUPPLIERS and MODELS. The only input here is the yellow model selector below.
| Part-supplier combos | Critical | Monitor | Low | Not scored | Models | Suppliers
| 6 | 2 | 3 | 1 | 0 | 2 | 6
RISK BY MODEL
| Model | Parts | Tissue? | Critical | Monitor | Low | Not scored | Max risk | Band
| Model A - Tissue Trainer (EXAMPLE) | 4 | Yes | 2 | 1 | 1 | 0 | 20.5 | CRITICAL
| Model B - Non-Tissue Kit (EXAMPLE) | 2 | No | 0 | 2 | 0 | 0 | 11.6 | MONITOR
MODEL DETAIL
Select model: | Model A - Tissue Trainer (EXAMPLE) |  |  | Parts of the selected model, highest risk first (red flags always on top).
# | Part number | Description | Type | Supplier | Impact | Likelihood | Risk | Band | Top driver | Red flag
1 | QOS-1113 | Fluid connector, luer | Non-Tissue: COTS | Qosina Corp. | 2 | 1.1 | 2.2 | CRITICAL (FLAG) | External & Location | EOL / obsolescence announced (COTS) | 4
2 | 666534 | Large Pork Belly | Tissue (APHIS) | Martin's Pork Products | 5 | 4.1 | 20.5 | CRITICAL | Sourcing & Backup |  | 2
3 | 666512 | Leaf Fat, porcine | Tissue (APHIS) | Parks Family Meats | 3 | 2.7 | 8.1 | MONITOR | External & Location |  | 1
4 | 666800-01 | Plate, thermoformed, Kydex | Non-Tissue: Custom | Advanced Plastiform | 3 | 2.2 | 6.6 | LOW | Capacity & Delivery |  | 3
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
TOP 10 RISKS - ALL MODELS
# | Model | Part number | Supplier | Risk | Band | Top driver
1 | Model A - Tissue Trainer (EXAMPLE) | QOS-1113 | Qosina Corp. | 2.2 | CRITICAL (FLAG) | External & Location |  |  |  |  | 4
2 | Model A - Tissue Trainer (EXAMPLE) | 666534 | Martin's Pork Products | 20.5 | CRITICAL | Sourcing & Backup |  |  |  |  | 2
3 | Model B - Non-Tissue Kit (EXAMPLE) | 666438 | SNP, Inc. | 11.6 | MONITOR | Sourcing & Backup |  |  |  |  | 5
4 | Model B - Non-Tissue Kit (EXAMPLE) | 666800-01 | Midland Plastics | 8.1 | MONITOR | Sourcing & Backup |  |  |  |  | 6
5 | Model A - Tissue Trainer (EXAMPLE) | 666512 | Parks Family Meats | 8.1 | MONITOR | External & Location |  |  |  |  | 1
6 | Model A - Tissue Trainer (EXAMPLE) | 666800-01 | Advanced Plastiform | 6.6 | LOW | Capacity & Delivery |  |  |  |  | 3
7
8
9
10

## PART_RISK
PART-SUPPLIER RISK REGISTER
One row per part-supplier combination. Cream = you enter/select. Gray = automatic. Score 1 (low risk) to 5 (high risk) using the SCORING_GUIDE anchors. A red flag forces the band to CRITICAL.
1. IDENTIFY THE PART |  |  |  |  | 2. SCORE THE PART (1-5) |  |  | 3. SUPPLIER SCORES (auto) |  | 4. IMPACT | 5. RED FLAG | RESULT (auto) |  |  |  | 6. ACTIONS & REVIEW
Model | Part_Number | Part_Description | Part_Type | Supplier | Sourcing_Backup | Quality_Compliance | Capacity_Delivery | Supplier_Stability | External_Location | Impact (1-5) | Red_Flag | Likelihood | Risk_Score | Risk_Band | Top_Driver | Mitigation / Notes | Last_Reviewed | srt | sel
Model A - Tissue Trainer (EXAMPLE) | 666512 | Leaf Fat, porcine | Tissue (APHIS) | Parks Family Meats | 2 | 3 | 2 | 3 | 4 | 3 |  | 2.7 | 8.1 | MONITOR | External & Location | EXAMPLE - replace with real data. Multi-sourced; permits current; watch defect rate (improving). | 2026-08-07 | 8.1 | 8.1
Model A - Tissue Trainer (EXAMPLE) | 666534 | Large Pork Belly | Tissue (APHIS) | Martin's Pork Products | 5 | 4 | 3 | 4 | 4 | 5 |  | 4.1 | 20.5 | CRITICAL | Sourcing & Backup | EXAMPLE - replace with real data. Sole source, declining quality trend: qualify backup harvest supplier, raise safety stock. | 2026-08-07 | 20.5001 | 20.5001
Model A - Tissue Trainer (EXAMPLE) | 666800-01 | Plate, thermoformed, Kydex | Non-Tissue: Custom | Advanced Plastiform | 2 | 2 | 3 | 2 | 2 | 3 |  | 2.2 | 6.6 | LOW | Capacity & Delivery | EXAMPLE - replace with real data. Alternates identified (Fictiv, Xometry); 8-week lead time. | 2026-08-07 | 6.6001 | 6.6001
Model A - Tissue Trainer (EXAMPLE) | QOS-1113 | Fluid connector, luer | Non-Tissue: COTS | Qosina Corp. | 1 | 1 | 1 | 1 | 2 | 2 | EOL / obsolescence announced (COTS) | 1.1 | 2.2 | CRITICAL (FLAG) | External & Location | EXAMPLE - replace with real data. Connector discontinued by OEM: last-time buy placed, replacement in qualification. | 2026-08-07 | 102.2001 | 102.2001
Model B - Non-Tissue Kit (EXAMPLE) | 666438 | Liquid, SB aqueous mixture | Non-Tissue: Custom | SNP, Inc. | 4 | 2 | 3 | 3 | 2 | 4 |  | 2.9 | 11.6 | MONITOR | Sourcing & Backup | EXAMPLE - replace with real data. Single source; second supplier (Brenntag) in qualification. | 2026-08-07 | 11.6001
Model B - Non-Tissue Kit (EXAMPLE) | 666800-01 | Plate, thermoformed, Kydex | Non-Tissue: Custom | Midland Plastics | 3 | 3 | 2 | 3 | 2 | 3 |  | 2.7 | 8.1 | MONITOR | Sourcing & Backup | EXAMPLE - replace with real data. New supplier - initial audit pending. | 2026-08-07 | 8.1001

## SUPPLIERS
SUPPLIERS
Score each supplier ONCE (two 1-5 scores). Every part linked to this supplier inherits these scores automatically on PART_RISK.
Supplier_Name | Location (City/State, Country) | Status | Supplier_Stability (1-5) | External_Location (1-5) | Certs / Permits (info) | Notes | Parts_Linked | Worst_Band
Parks Family Meats | Warsaw, NC, USA | Approved | 3 | 4 | APHIS specimen permit (exp 12/2026); FDA FSIS | EXAMPLE - small local slaughterhouse; strong relationship. | 1 | MONITOR
Martin's Pork Products | Falcon, NC, USA | Approved | 4 | 4 | APHIS specimen permit (exp 5/2026); FDA FSIS | EXAMPLE - small family business; past power/sanitation issues; flood-prone area. | 1 | CRITICAL
Advanced Plastiform | NC, USA | Approved | 2 | 2 | ISO 9001 | EXAMPLE - established plastics former. | 1 | LOW
Midland Plastics | WI, USA | New | 3 | 2 | ISO 9001 (to verify) | EXAMPLE - new supplier, audit pending. | 1 | MONITOR
Qosina Corp. | Ronkonkoma, NY, USA | Intuitive Corporate | 1 | 2 | ISO 9001, ISO 13485 | EXAMPLE - large catalog distributor. | 1 | CRITICAL
SNP, Inc. | USA | Approved | 3 | 2 | ISO 9001 | EXAMPLE - chemical blender; single site. | 1 | MONITOR

## MODELS
MODELS
Add one row per model / project. Everything except the first two columns fills in automatically from PART_RISK.
Model_Name | Description | Has_Tissue_Parts | Parts | Critical | Monitor | Low | Not_Scored | Max_Risk | Model_Band
Model A - Tissue Trainer (EXAMPLE) | Example model containing tissue and non-tissue parts. | Yes | 4 | 2 | 1 | 1 | 0 | 20.5 | CRITICAL
Model B - Non-Tissue Kit (EXAMPLE) | Example model containing non-tissue parts only. | No | 2 | 0 | 2 | 0 | 0 | 11.6 | MONITOR

## SCORING_GUIDE
SCORING GUIDE
RISK = LIKELIHOOD x IMPACT. Likelihood = weighted average of the five 1-5 criteria below. Impact = how bad it is for the model if this part-supplier fails (1-5). Risk runs 1-25.
Every criterion uses the same simple rule: 1 = low risk, 3 = medium, 5 = high. Score 2 or 4 when reality sits between the anchors. If you can't answer, leave it blank - the row shows NOT SCORED instead of a wrong number.
WEIGHTS (editable - cream cells; must total 100%)
Criterion | Weight | The question it answers
Sourcing & Backup | 25% | Could we get this part somewhere else, and how fast?
Quality & Compliance | 25% | Will the part be good and legal (permits, certs, defect history)?
Capacity & Delivery | 20% | Can they make enough, on time, and absorb a surge?
Supplier Stability | 20% | Will this supplier still be here, and do we matter to them? (scored on SUPPLIERS)
External & Location | 10% | What can hit them from outside - weather, logistics, borders? (scored on SUPPLIERS)
Total (must be 100%) | 100% | Defaults mirror the weight logic of the previous tool (Quality 25%, Relationship 20%, Ops 15-20%...), collapsed to five criteria.
RISK BANDS (editable thresholds)
Band | Threshold | Action
CRITICAL | 15 | Risk >= 15 (or any red flag): act now - qualify backup, build stock, escalate.
MONITOR | 7 | Risk 7-14.9: watch actively, have a contingency plan, review quarterly.
LOW | < 7 | Standard supplier management, review yearly.
Cutoffs follow the standard 5x5 risk-matrix convention (ISO 31000 / IEC 31010): 15-25 red, 7-14 yellow, 1-6 green.
SOURCING & BACKUP (part-level)
Score |  | What it looks like
1 |  | Multiple approved suppliers; switching is easy and fast.
3 |  | Single source today, but a backup is identified and could be qualified in under ~3 months.
5 |  | Sole source, no backup identified; switching means 6+ months of requalification.
QUALITY & COMPLIANCE (part-level)
Score |  | What it looks like
1 |  | All certs/permits current, no significant issues in 12 months, stable or improving trend.
3 |  | Certs/permits current but with gaps (e.g. state-only inspection, no SQA signed, occasional defects, audit due).
5 |  | Expired/missing permit or certification, repeated defects, declining trend, or open major CAPA.
Tissue parts: think specimen/APHIS permits, FSIS inspection level, audit status, recent lot rejections.
Non-tissue parts: think ISO 9001/13485, audit results, defect (PPM) history, open CAPAs, process capability for custom parts.
CAPACITY & DELIVERY (part-level)
Score |  | What it looks like
1 |  | Plenty of headroom (supplier under ~70% loaded), lead time comfortably meets need, deliveries on time.
3 |  | Busy (~70-85% loaded) but can cover a 125% surge with notice; lead time acceptable.
5 |  | Near or over capacity (>85%), cannot cover a surge, long or erratic lead times, late deliveries.
SUPPLIER STABILITY (supplier-level, scored once on SUPPLIERS)
Score |  | What it looks like
1 |  | Established, healthy business; strong relationship; we are a meaningful customer to them.
3 |  | Small or newer business; generally reliable; we are one customer among many.
5 |  | Signs of instability (staffing, cash, ownership, key-person risk), strained relationship, phase-out risk, or our volume is insignificant to them.
Most of our suppliers are small local businesses - judge stability from what you see and hear (staffing, maintenance, responsiveness), not financial statements.
EXTERNAL & LOCATION (supplier-level, scored once on SUPPLIERS)
Score |  | What it looks like
1 |  | Low-risk location, robust logistics, no special transport needs.
3 |  | Some exposure: weather-prone region, single logistics route, or cold-chain need with a capable partner.
5 |  | High exposure: flood/hurricane zone, remote or single-road access, cross-border / tariff / sanction exposure, or unreliable cold chain.
IMPACT (part-level: if this part stops, how bad for the model?)
Score |  | What it looks like
1 |  | Cosmetic or minor part; substitute on the shelf; negligible spend.
3 |  | Production slows; workaround or inventory buffer exists; moderate spend.
5 |  | Model cannot ship; no substitute; high spend or long requalification of an alternative.
RED FLAGS (any flag forces the band to CRITICAL, whatever the score)
Flag |  | Why it overrides the score
Permit / APHIS non-compliance (tissue) |  | A tissue part without a valid permit cannot legally be used - no score can compensate.
Stop-ship quality failure |  | An active stop-ship means supply is already interrupted.
Supplier exiting or disapproved |  | Supply will end regardless of how well it performs today.
EOL / obsolescence announced (COTS) |  | The catalog part is going away - a replacement must be qualified.
Stock-out before recovery (TTS < TTR) |  | If inventory runs out before the supplier could recover from a disruption, any disruption stops the line.
Capacity exceeded (no headroom) |  | Demand already exceeds what the supplier can make.
Other (see notes) |  | Judgment call - explain in the Notes column.
METHOD & SOURCES (why the model is built this way)
- Two-axis logic (supply risk x business impact per purchased item): Kraljic, 'Purchasing Must Become Supply Management', Harvard Business Review, 1983 - the standard purchasing-portfolio segmentation.
- Likelihood x Impact on a 5x5 matrix with 15/7 band cutoffs: ISO 31000 / IEC 31010 risk-assessment convention; same probability-x-severity logic as ISO 14971 used in medical device risk files.
- 'Stock-out before recovery' red flag: Simchi-Levi's Time-to-Recover / Time-to-Survive framework (HBR 2014; used by Ford, Cisco, UN) - a node where TTS < TTR exposes the firm in ANY disruption.
- Part-level (not just supplier-level) assessment and the Last_Reviewed column: ISO 13485 clause 7.4 / FDA QMSR require supplier controls proportionate to the EFFECT OF THE PURCHASED PRODUCT on device quality, plus a dated ongoing monitoring record.
- Red flags = knock-out criteria, standard practice in supplier qualification: some conditions (invalid permit, EOL, stop-ship) invalidate a good average score.
WHAT CHANGED vs THE PREVIOUS TOOLS (design notes)
- The 7 weighted pillars + 10 override rules + dependency multipliers of supplier_risk_tool_v12 are collapsed into 5 plain criteria, 1 impact score and 7 red flags.
- Source dependency (sole/single/dual) no longer multiplies the score - it IS the Sourcing & Backup criterion, weighted 25%.
- Altman Z-Score, PPM formulas and Cpk thresholds are gone as inputs: our suppliers are mostly small private businesses where those numbers don't exist or aren't reliable. They remain as things to consider inside the 1-5 anchors.
- Financial + Relationship pillars merged into one supplier-level 'Supplier Stability' score; Geopolitical + Environmental merged into 'External & Location'. Cybersecurity dropped as a scored pillar (was 5%) - note IP exposure in supplier Notes if relevant.
- Risk = Likelihood x Impact (5x5 matrix, same logic as ISO 14971 risk thinking) so a critical part at a good supplier and a minor part at a bad supplier are separated - the part-level view the old supplier-level tool couldn't give.
- Supplier-level scores live on SUPPLIERS and are entered once; part rows inherit them, so adding the 10th part from a supplier costs seconds, not another 100-column row.
- Band thresholds (>=15 CRITICAL, >=7 MONITOR) follow the standard 5x5 matrix convention; the previous tool's 0-100 bands (>=80/>=50) served the same purpose.

## LISTS
Part_Types | Score_1_5 | Red_Flags | Supplier_Status | Driver_Names
Tissue (APHIS) | 1 | Permit / APHIS non-compliance (tissue) | New | Sourcing & Backup
Tissue (Non-APHIS) | 2 | Stop-ship quality failure | Approved | Quality & Compliance
Non-Tissue: Custom | 3 | Supplier exiting or disapproved | Intuitive Corporate | Capacity & Delivery
Non-Tissue: COTS | 4 | EOL / obsolescence announced (COTS) | Conditional | Supplier Stability
| 5 | Stock-out before recovery (TTS < TTR) | Phase-Out | External & Location
|  | Capacity exceeded (no headroom) | Disapproved
Other (see notes)
This sheet feeds the dropdowns. Add options here if you need more.