## Read Me
Supplier Scorecard — how to use
What this workbook does
Logs every project you run with a supplier, scores it on Cost, Quality, Lead time and Responsiveness (1–5), and rolls it all up so you can see what each supplier is giving you — overall and per process.
Logging a project (Score Log tab)
1. One row per project / PO. Enter the date, project name, and pick Supplier and Process from the dropdowns.
2. Score the four criteria 1–5 — the Rubric tab defines what each number means. Each score has its own notes column; use it for the 'why'.
3. Overall is calculated automatically from the weights in Settings (defaults: Quality 30%, Cost 25%, Lead time 25%, Responsiveness 20% — edit the yellow cells anytime).
4. Cost data and Delivery data columns are optional — leave them blank when you don't have the numbers. When filled, the sheet computes cost variance, days late, and on-time %.
Reading the Dashboard tab
Supplier scorecard: one line per supplier — project count, average score per criterion, weighted overall, on-time %, average cost variance, and the date last used. The chart compares overall averages.
By-process comparison: average overall score for each supplier × process pairing, so you can see who is strongest at injection molding vs 3D printing vs thermoforming.
Color legend
White cells = you type. Yellow cells (Settings) = editable defaults. Gray-filled columns = automatic, don't type in them. Gray italic rows = example data — replace with real entries.
Scores are shaded red (1) → yellow (3) → green (5) automatically.
Adding suppliers and processes
New supplier: add a row in the Suppliers tab (column A feeds the dropdown). New process/part type: add it in Settings, column D. Both dropdowns update automatically.
Capacity (pre-wired ranges)
200 log rows · 30 suppliers · 30 processes. Dashboard chart shows the first 15 suppliers; the by-process grid shows the first 10 suppliers × first 20 processes. If you outgrow any of these, ask Claude to extend them.
Built with Claude, 2026-07-25. Example data and default weights were set for illustration — every assumption is editable.

## Score Log
Supplier Score Log |  |  |  | One row per project. White cells = you type; gray columns = automatic. Gray italic rows are examples — replace them. Rubric tab defines the 1–5 scale.
Project info |  |  |  |  | Scores 1–5 & notes (Overall is automatic) | [8 empty] | Cost data (optional) |  |  | Delivery data (optional)
Date | Project | Supplier | Process / part type | Part description | Cost (1–5) | Cost notes | Quality (1–5) | Quality notes | Lead time (1–5) | Lead time notes | Responsiveness (1–5) | Responsiveness notes | Overall (auto) | Quoted cost | Actual cost | Cost var % (auto) | Promised delivery | Actual delivery | Days late (auto) | On time? (auto) | General notes
2026-06-01 | Gyn 2.0 | Fictiv | Injection molding | Uterus Insert | 4 | 35% (average) under comparable quotes | 5 | Zero rejects at incoming inspection | 4 | Parts came on time. | 5 | 24 hours spam of replies and thorough. | 4.5 | 20585.77 | 6939 | -66.29% | 2026-07-13 | 2026-07-13 | 0 | Yes | Good quality overall, communications, lead time and responsiveness
2026-06-01 | Gyn 2.0 | Fictiv | Injection molding | End Plate | 4 | 35% (average) under comparable quotes | 5 | Zero rejects at incoming inspection | 4 | Parts came on time. | 5 | 24 hours spam of replies and thorough. | 4.5 | 20585.77 | 6939 | -66.29% | 2026-07-13 | 2026-07-13 | 0 | Yes | Good quality overall, communications, lead time and responsiveness
2026-01-05 |  | Advanced Plastiform | Thermoforming | Suppine chest base | [7 empty] | Responsive to inquiries and provided revised timelines, but Intuitive frequently had to request status updates

## Dashboard
Supplier Dashboard
Everything on this tab is automatic — it updates as you log projects. '–' means no data yet.
Supplier scorecard
Supplier | Projects | Avg Cost | Avg Quality | Avg Lead time | Avg Responsiveness | Avg Overall | On-time % | Avg cost var % | Last project
Fictiv | 2 | 4 | 5 | 4 | 5 | 4.5 | 100% | -66.29% | 2026-06-01
Advanced Plastiform | 1 | – | – | – | – | – | – | – | 2026-01-05
By-process comparison — average overall score
Rows mirror the process list in Settings (first 20); columns mirror the first 10 suppliers. Blank = no projects yet for that pairing.
Process / part type | Projects | Fictiv | Advanced Plastiform
Thermoforming | 1
Injection molding | 2 | 4.5
3D printing (FDM) | 0
3D printing (SLA) | 0
3D printing (SLS) | 0
PVA | 0
CNC machining | 0
Vacuum casting | 0
Sheet metal | 0
Extrusion | 0
Casting | 0
Other | 0
Compression Molding | 0
Formulas:
Last project = IF([Supplier]="","",IF([Projects]=0,"–",MAXIFS('Score Log'!$A4:A204,'Score Log'!$C4:C204,[Supplier])))

## Risk Suggestions
Risk Suggestions - feed for the Part-Supplier Risk Model
FULLY AUTOMATIC: every distinct Part + Supplier pair in the Score Log gets exactly one line here, in order of first appearance - log projects one row per part and combos appear by themselves. Translation: risk = 6 - average performance (scorecard 5 = excellent -> risk 1 = low), rounded and clamped to 1-5. Type the suggested values into the PART_RISK tab of Part_Supplier_Risk_Model - a starting point, not an override.
PART-SUPPLIER COMBOS (auto from Score Log) |  |  | SCORECARD PERFORMANCE FOR THE COMBO (auto, 5 = excellent) | [6 empty] | SUGGESTED RISK ENTRIES FOR PART_RISK (1 = low risk ... 5 = high) | [5 empty] | first | ord
Part (from Score Log) | Supplier | Process / part type | Projects | Avg Cost | Avg Quality | Avg Lead time | Avg Responsiveness | Avg Overall | On-time % | Quality_Compliance (suggest) | Capacity (suggest) | Supplier_Stability (suggest) | cA | rA | lr | 1 | 1
Uterus Insert | Fictiv | Injection molding | 1 | 4 | 5 | 4 | 5 | 4.5 | 100% | 1 | 2 | 2 | 4 | 5 | 4 | 1 | 2
End Plate | Fictiv | Injection molding | 1 | 4 | 5 | 4 | 5 | 4.5 | 100% | 1 | 2 | 2 | 4 | 5 | 5 | 1 | 3
Suppine chest base | Advanced Plastiform | Thermoforming | 1 | - | - | - | - | - | 0% | - | - | - |  |  | 6 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
HOW THIS TAB WORKS | [15 empty] | 0
Rows appear automatically: each distinct Part + Supplier pair in the Score Log = one line (first 60 combos; log rows without a Part description are not listed). Keep part names consistent in the log - 'Uterus Insert' and 'uterus insert' would count as two parts. | [15 empty] | 0
Quality_Compliance <- 6 - avg Quality of THIS combo. What they delivered on this part is direct evidence for its quality risk. | [15 empty] | 0
Capacity <- 6 - avg Lead time of THIS combo. Observed delivery performance is the visible side of capacity; sanity-check against On-time %. | [15 empty] | 0
Supplier_Stability <- 6 - average(Responsiveness, Cost) across ALL the supplier's projects, regardless of part - stability is about the supplier as a business. Cost has no part-level column in the risk register, but erratic pricing and poor cost transparency - like slow communication - are stability evidence. | [15 empty] | 0
No scorecard equivalent - score these by judgment in the master model: Sourcing_Backup (do alternatives exist?), External_Factors (location, logistics, borders), Impact (what the part means to the model), Qty_per_Model / volume. | [15 empty] | 0
Suggestions round to the nearest whole score and clamp to 1-5. Few projects behind a combo (see Projects column) = thin evidence - weigh it accordingly. | [15 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Suppliers
Supplier directory |  |  | One row per supplier. The Supplier dropdown in Score Log pulls from column A. Gray italic rows are examples — replace them.
Supplier name | Location | Contact person | Email / phone | Processes offered | Notes
Fictiv |  | Zoran Savic | zoran.savic@fictiv.com | Injection molding, Thermoforming, 3D printing (FDM / SLA), PVA
Advanced Plastiform

## Rubric
Scoring rubric — what 1 to 5 means
Score each criterion at project close. When you're between two numbers, pick the lower one and explain in the notes column.
Criterion | 1 — Poor | 2 — Weak | 3 — Acceptable | 4 — Good | 5 — Excellent
Cost | Far above market; surprise charges; no cost transparency. | Above comparable quotes; extras billed without warning. | In line with market; small deviations, explained when raised. | Competitive; quotes hold through the project; flags cost drivers early. | Best value; proactive cost-down ideas; transparent cost breakdowns.
Quality | Major defects; lot rejected or unusable; no corrective action. | Repeated defects; rework needed; corrective action is slow. | Occasional minor defects; fixed when we raise them. | Meets spec consistently; rare cosmetic issues; solid first articles. | Zero defects; first article right the first time; strong QC documentation.
Lead time | Very late (weeks or >50% overrun); no warning given. | Late with little notice; promised dates slip repeatedly. | Mostly on time; small slips, communicated in advance. | On time; realistic promises; good visibility of schedule. | On time or early, every time; absorbs rush requests without drama.
Responsiveness | Days of silence; we chase constantly; unclear who owns our account. | Slow replies; vague answers; hard to reach when problems appear. | Replies within ~48 h; adequate technical answers. | Same/next-day replies; clear technical communication; proactive updates. | Immediate expert answers; flags problems before we ask; acts like a partner.

## Settings
Settings & Lists
Score weights |  | Edit the yellow cells. Total must equal 100%. (Defaults set 2026-07-25 with Oscar — quality weighted highest.) | Process / part type list (add more below — dropdowns update automatically)
Cost | 25% |  | Thermoforming
Quality | 30% |  | Injection molding
Lead time | 25% |  | 3D printing (FDM)
Responsiveness | 20% |  | 3D printing (SLA)
Total | 100% |  | 3D printing (SLS)
PVA
CNC machining
Vacuum casting
Sheet metal
Extrusion
Casting
Other
Compression Molding