## Slide 1
Finding and onboarding a tissue supplier — the plan
Five stages. Each one starts only when its entry gate is true, produces a deliverable, and closes on an exit gate — the evidence anyone can check.
Sep 30, 2026
IDENTIFIED
Oct 29
calls done
Nov 2 – Dec 18
Calls-visits (done adhoc)
Dec 7 – Jan 22
pelvic pilot
Jan 27, 2027
SELECTED
Feb 2 – Mar 27
onboarding
Jun -Jul, 2027
reliable product
review
1
IDENTIFY Possible SHs
Sep 2026 — done
STARTS WHEN
The brief (models A / B-T, the gates, 140–220 lb, 120 mi from Durham) and USDA / NCDA primary data.
WHAT HAPPENS
Every slaughter plant in NC / SC / VA / TN verified, scored on both operating models, bounded on volume.
DELIVERABLE
Supplier Study workbook + one-page shortlist memo.
DONE WHEN
Supplier Engineer and Purchasing Manager have each picked 3.
2
QUALIFY
Oct 1 → Dec 18
STARTS WHEN
Workbook shared; weekly pick meeting held; call script in hand; caller = Purchasing Manager.
WHAT HAPPENS
Calls by Oct 29 — three questions, no business-model talk → joint go / no-go → NDA → visits Nov 2–Dec 18: floor walk, model, spec, how we pay.
DELIVERABLE
Call logs, go / no-go record, signed NDAs, one visit report per plant.
DONE WHEN
A plant rated "qualified to pilot".
3
TEST
Dec 7 → Jan 22
STARTS WHEN
Qualified plant; paid pilot agreement; (pelvic, aorta, bariatric) spec signed; inspector named; cold chain arranged.
WHAT HAPPENS
Supervised pelvic harvests; every block inspected for quality, size and completeness; chill and transport measured; real cost per block.
DELIVERABLE
Pilot report: yield, inspection results, cost vs. model.
DONE WHEN
≥ 30 inspected units over 2 consecutive harvest days at ≥ 95 % first-pass yield.
4
SELECT
by Jan 27
STARTS WHEN
Pilot report; Quality sign-off; commercial terms in writing.
WHAT HAPPENS
Evaluation and qualification results reviewed; the supplier that passes is selected for onboarding.
DELIVERABLE
Selection, resulting documents — the evidence the supplier passed, terms, risks.
DONE WHEN
Inspection signed by Supplier Engineering, Quality and Purchasing; approved-supplier record created.
5
ONBOARD
Feb 2 → TBD
STARTS WHEN
Signed selection memo; contract draft; freezers ordered; harvest days proposed; training plan if their crew harvests.
WHAT HAPPENS
Onboarding
DELIVERABLE
Onboarded supplier record
DONE WHEN
Onboarding team finishes, out of our control.
Notes: Five-stage supplier qualification plan with entry gates, deliverables and exit gates. Dates as agreed 2026-09-28: calls complete Oct 29; visits Nov 2–Dec 18; pilot Dec 7–Jan 22; selection by Jan 27; onboarding from Feb 2; reliable-product review Jun–Jul 2027. Once a supplier passes evaluation and qualification it is onboarded — there is no bidding round.